## Slide 1
Kick-off Meeting (23rd January)
Draft release version 2.0.0 for validation by the WG (25th June)
Working Group Meeting (23rd February)
Subject: Presentation of the new mission, considerations on the scope and methodology.
Working Group Meeting (28th March)
Subject: PoC validation of the approach, the use case and the expected results.
Working Group Meeting (16th May)
Subject: Revision of the ontology, conceptual model and design considerations.
Working Group Meeting (21st June)
Subject: Revision of the ontology, OWL implementation and results of the PoC.
9th March:
  1. Glossary acceptance by the Working Group.
  2. Sample Competency Questions available for the WG.
23-26 March:
  Conceptual data model available for revision by WG.
14th May: PoC and new version of the conceptual data model available for revision by WG.
21st June: PoC available for revision by WG.